## Release Schedule Platform
Release Version | Sprint Name | SOW Approval Date | Sprint Start | Sprint End | Sprint length (days) | Notes | Days from sprint end to UAT | UAT Release | Days between UAT release and sign off | UAT Feedback Deadline + Regression Starts | Days to remedy UAT feedback | Production Release Date (4pm PST) | Days from sprint start to production release
2.63.0 | Able | 2019-10-31 | 2019-11-06 | 2019-11-19 | 13
2.63.1 | Best | 2019-11-14 | 2019-11-20 | 2019-12-10 | 20 | Long Sprint, Moved for stat | 17 | 2019-12-27 | 26 | 2020-01-22 | 17 | 2020-02-08 | 94
2.64.0 | Cold | 2019-12-05 | 2019-12-11 | 2019-12-31 | 20 | Long Sprint
2.64.1 | Deep | 2019-12-26 | 2020-01-01 | 2020-01-14 | 13 |  | 16 | 2020-01-30 | 27 | 2020-02-26 | 17 | 2020-03-14 | 94
2.65.0 | Anaconda | 2020-01-09 | 2020-01-15 | 2020-01-28 | 13
2.65.1 | Beluga | 2020-01-23 | 2020-01-29 | 2020-02-11 | 13 |  | 16 | 2020-02-27 | 34 | 2020-04-01 | 17 | 2020-04-18 | 94
2.66.0 | Chimpanzee | 2020-02-06 | 2020-02-12 | 2020-02-25 | 13
2.66.1 | Flamingo | 2020-02-20 | 2020-02-26 | 2020-03-10 | 13 | Moved for stat | 23 | 2020-04-02 | 20 | 2020-04-22 | 17 | 2020-05-09 | 87
2.67.0 | Hippoptamus | 2020-03-05 | 2020-03-11 | 2020-03-24 | 13
2.67.1 | Indri | 2020-03-19 | 2020-03-25 | 2020-04-07 | 13 |  | 16 | 2020-04-23 | 41 | 2020-06-03 | 17 | 2020-06-20 | 101
2.68.0 | Jerboa | 2020-04-02 | 2020-04-08 | 2020-04-21 | 13
2.68.1 | Koala | 2020-04-16 | 2020-04-22 | 2020-05-05 | 13 | Feedback deadline moved for stat | 30 | 2020-06-04 | 28 | 2020-07-02 | 16 | 2020-07-18 | 101
2.69.0 | Llama | 2020-04-30 | 2020-05-06 | 2020-05-19 | 13
2.69.1 | Meerkat | 2020-05-14 | 2020-05-20 | 2020-06-02 | 13 |  | 30 | 2020-07-02 | 27 | 2020-07-29 | 17 | 2020-08-15 | 101
2.70.0 | Narwhal | 2020-05-28 | 2020-06-03 | 2020-06-16 | 13
2.70.1 | Orangutan | 2020-06-11 | 2020-06-17 | 2020-06-30 | 13 |  | 30 | 2020-07-30 | 34 | 2020-09-02 | 17 | 2020-09-19 | 108
2.71.0 | Platypus | 2020-06-25 | 2020-07-01 | 2020-07-14 | 13
2.71.1 | Quokka | 2020-07-09 | 2020-07-15 | 2020-07-28 | 13 |  | 37 | 2020-09-03 | 27 | 2020-09-30 | 17 | 2020-10-17 | 108
2.72.0 | Rhino | 2020-07-23 | 2020-07-29 | 2020-08-11 | 13
2.72.1 | Sloth | 2020-08-06 | 2020-08-12 | 2020-08-25 | 13 |  | 37 | 2020-10-01 | 27 | 2020-10-28 | 17 | 2020-11-14 | 108
2.73.0 | Tiger | 2020-08-20 | 2020-08-26 | 2020-09-08 | 13
2.73.1 | Uakari | 2020-09-03 | 2020-09-09 | 2020-09-22 | 13 |  | 37 | 2020-10-29 | 34 | 2020-12-02 | 17 | 2020-12-19 | 115
2.74.0 | Vaquita | 2020-09-17 | 2020-09-23 | 2020-10-06 | 13
2.74.1 | Wombat | 2020-10-01 | 2020-10-07 | 2020-10-20 | 13 |  | 44 | 2020-12-03 | 27 | 2020-12-30 | 17 | 2021-01-16 | 115
2.75.0 | Xenosaurus Platycep | 2020-10-15 | 2020-10-21 | 2020-11-03 | 13
2.75.1 | Yeti | 2020-10-29 | 2020-11-04 | 2020-11-17 | 13 | Moved for stat | 50 | 2021-01-06 | 28 | 2021-02-03 | 17 | 2021-02-20 | 122
2.76.0 | Zebra | 2020-11-12 | 2020-11-18 | 2020-12-01 | 13
2.76.1 | Arcteryx | 2020-11-26 | 2020-12-02 | 2020-12-15 | 13 |  | 44 | 2021-01-28 | 34 | 2021-03-03 | 17 | 2021-03-20 | 122
2.77.0 | Big Agnes | 2020-12-10 | 2020-12-16 | 2020-12-29 | 13
2.77.1 | Cotopaxi | 2020-12-24 | 2020-12-30 | 2021-01-19 | 20 | Long sprint, Good Friday is on 2nd | 37 | 2021-02-25 | 27 | 2021-03-24 | 10 | 2021-04-03 | 108
2.78.0 | Darn Tough | 2021-01-14 | 2021-01-20 | 2021-02-09 | 20 | Long sprint
2.78.1 | Engineered Iron | 2021-02-04 | 2021-02-10 | 2021-02-23 | 13 |  | 17 | 2021-03-12 | 26 | 2021-04-07 | 10 | 2021-04-17 | 87
2.79.0 | Fjallraven | 2021-02-18 | 2021-02-24 | 2021-03-09 | 13
2.79.1 | Garmin | 2021-03-04 | 2021-03-10 | 2021-03-23 | 13 |  | 16 | 2021-04-08 | 20 | 2021-04-28 | 10 | 2021-05-08 | 73
2.80.0 | Helinox | 2021-03-18 | 2021-03-24 | 2021-04-06 | 13
2.80.1 | Icebreaker | 2021-04-01 | 2021-04-07 | 2021-04-20 | 13 |  | 16 | 2021-05-06 | 20 | 2021-05-26 | 10 | 2021-06-05 | 73
2.81.0 | Jetboil | 2021-04-15 | 2021-04-21 | 2021-05-04 | 13
2.81.1 | Komperdell | 2021-04-29 | 2021-05-05 | 2021-05-18 | 13 |  | 23 | 2021-06-10 | 20 | 2021-06-30 | 10 | 2021-07-10 | 80
2.82.0 | Leki | 2021-05-13 | 2021-05-19 | 2021-06-01 | 13
2.82.1 | Marmot | 2021-05-27 | 2021-06-02 | 2021-06-15 | 13 |  | 23 | 2021-07-08 | 20 | 2021-07-28 | 10 | 2021-08-07 | 80
2.83.0 | Nemo | 2021-06-10 | 2021-06-16 | 2021-06-29 | 13
2.83.1 | Osprey | 2021-06-24 | 2021-06-30 | 2021-07-20 | 20 | Long sprint | 23 | 2021-08-12 | 20 | 2021-09-01 | 10 | 2021-09-11 | 87
2.84.0 | Patagonia | 2021-07-15 | 2021-07-21 | 2021-08-03 | 13
2.84.1 | Quicksilver | 2021-07-29 | 2021-08-04 | 2021-08-17 | 13 |  | 30 | 2021-09-16 | 20 | 2021-10-06 | 10 | 2021-10-16 | 87
2.85.0 | Rab | 2021-08-12 | 2021-08-18 | 2021-08-31 | 13
2.85.1 | Sea to Summit | 2021-08-26 | 2021-09-01 | 2021-09-14 | 13 |  | 23 | 2021-10-07 | 20 | 2021-10-27 | 10 | 2021-11-06 | 80
2.86.0 | Tentree | 2021-09-09 | 2021-09-15 | 2021-09-28 | 13
2.86.1 | Under Armour | 2021-09-23 | 2021-09-29 | 2021-10-12 | 13 |  | 31 | 2021-11-12 | 19 | 2021-12-01 | 10 | 2021-12-11 | 87
2.87.0 | Vasque | 2021-10-07 | 2021-10-13 | 2021-10-26 | 13
2.87.1 | Wigwam | 2021-10-21 | 2021-10-27 | 2021-11-16 | 20 | Long sprint | 23 | 2021-12-09 | 20 | 2021-12-29 | 10 | 2022-01-08 | 87
2.88.0 | Xero Shoes | 2021-11-11 | 2021-11-17 | 2021-11-30 | 13
2.88.1 | YETI | 2021-11-25 | 2021-12-01 | 2021-12-14 | 13 |  | 23 | 2022-01-06 | 20 | 2022-01-26 | 10 | 2022-02-05 | 80
2.89 | Zamberlan | 2021-12-09 | 2021-12-15 | 2021-12-28 | 13
2.89 | Atwell | 2021-12-23 | 2021-12-29 | 2022-01-11 | 13 |  | 23 | 2022-02-03 | 20 | 2022-02-23 | 10 | 2022-03-05 | 80
2.9 | Blackcomb | 2022-01-06 | 2022-01-12 | 2022-02-01 | 20 | Long sprint
2.9 | Currie | 2022-01-27 | 2022-02-02 | 2022-02-15 | 13 |  | 23 | 2022-03-10 | 20 | 2022-03-30 | 10 | 2022-04-09 | 87
2.91 | Diamond Head | 2022-02-10 | 2022-02-16 | 2022-03-01 | 13
2.91 | Elk | 2022-02-24 | 2022-03-02 | 2022-03-15 | 13 |  | 23 | 2022-04-07 | 20 | 2022-04-27 | 10 | 2022-05-07 | 80
2.92 | Flora | 2022-03-10 | 2022-03-16 | 2022-03-29 | 13
2.92 | Garibaldi | 2022-03-24 | 2022-03-30 | 2022-04-12 | 13 |  | 23 | 2022-05-05 | 20 | 2022-05-25 | 10 | 2022-06-04 | 80
2.93 | Harvey | 2022-04-07 | 2022-04-13 | 2022-04-26 | 13
2.93 | Illal | 2022-04-21 | 2022-04-27 | 2022-05-10 | 13 |  | 30 | 2022-06-09 | 20 | 2022-06-29 | 10 | 2022-07-09 | 87
2.94 | Joffre | 2022-05-05 | 2022-05-11 | 2022-05-31 | 20 | Long Sprint (Reduce PROD release Window)
2.94 | Killam | 2022-05-26 | 2022-06-01 | 2022-06-14 | 13 |  | 9 | 2022-06-23 | 20 | 2022-07-13 | 10 | 2022-07-23 | 73
2.95 | Little Goat | 2022-06-09 | 2022-06-15 | 2022-06-28 | 13
2.95 | Monashee | 2022-06-23 | 2022-06-29 | 2022-07-12 | 13 |  | 2 | 2022-07-14 | 20 | 2022-08-03 | 10 | 2022-08-13 | 59
2.96 | Needle | 2022-07-07 | 2022-07-13 | 2022-07-26 | 13
2.96 | Ossa | 2022-07-21 | 2022-07-27 | 2022-08-09 | 13 |  | 2 | 2022-08-11 | 20 | 2022-08-31 | 10 | 2022-09-10 | 59
2.97 | Panorama | 2022-08-04 | 2022-08-10 | 2022-08-23 | 13
2.97 | Quarry Rock | 2022-08-18 | 2022-08-24 | 2022-09-13 | 20 | Long Sprint | 2 | 2022-09-15 | 20 | 2022-10-05 | 10 | 2022-10-15 | 66
2.98 | Robson | 2022-09-08 | 2022-09-14 | 2022-09-27 | 13
2.98 | Saint Marks | 2022-09-22 | 2022-09-28 | 2022-10-11 | 13 |  | 9 | 2022-10-20 | 20 | 2022-11-09 | 10 | 2022-11-19 | 66
2.99 | Trophy | 2022-10-06 | 2022-10-12 | 2022-10-25 | 13
2.99 | Unnecessary | 2022-10-20 | 2022-10-26 | 2022-11-15 | 20 | Long Sprint | 2 | 2022-11-17 | 20 | 2022-12-07 | 10 | 2022-12-17 | 66
2.1 | Valhalla | 2022-11-10 | 2022-11-16 | 2022-11-29 | 13
2.1 | Waddington | 2022-11-24 | 2022-11-30 | 2022-12-13 | 13 |  | 2 | 2022-12-15 | 20 | 2023-01-04 | 10 | 2023-01-14 | 59
2.101 | Wedgemount | 2022-12-08 | 2022-12-14 | 2022-12-27 | 13
2.101 | Yak | 2022-12-22 | 2022-12-28 | 2023-01-10 | 13 |  | 6 | 2023-01-16 | 20 | 2023-02-05 | 10 | 2023-02-15 | 63
2.102 | Zoa | 2023-01-05 | 2023-01-11 | 2023-01-24 | 13
2.102 | Aloe Vera | 2023-01-19 | 2023-01-25 | 2023-02-07 | 13 |  | 2 | 2023-02-09 | 20 | 2023-03-01 | 10 | 2023-03-11 | 59
2.103 | Banana | 2023-02-02 | 2023-02-08 | 2023-02-21 | 13
2.103 | Corpse Flower | 2023-02-16 | 2023-02-22 | 2023-03-14 | 20 | Long Sprint | 2 | 2023-03-16 | 20 | 2023-04-05 | 10 | 2023-04-15 | 66
2.104 | Dracaena Draco | 2023-03-09 | 2023-03-15 | 2023-03-28 | 13
2.104 | Elephant Ear | 2023-03-23 | 2023-03-29 | 2023-04-11 | 13 |  | 2 | 2023-04-13 | 20 | 2023-05-03 | 10 | 2023-05-13 | 59
2.105 | Fern | 2023-04-06 | 2023-04-12 | 2023-04-25 | 13
2.105 | Goldfish | 2023-04-20 | 2023-04-26 | 2023-05-09 | 13 |  | 2 | 2023-05-11 | 20 | 2023-05-31 | 10 | 2023-06-10 | 59
2.106 | Happy Bean | 2023-05-04 | 2023-05-10 | 2023-05-23 | 13
2.106 | Ivy | 2023-05-18 | 2023-05-24 | 2023-06-13 | 20 | Long Sprint | 2 | 2023-06-15 | 20 | 2023-07-05 | 10 | 2023-07-15 | 66
2.107 | Jade | 2023-06-08 | 2023-06-14 | 2023-06-27 | 13
2.107 | Kohleria | 2023-06-22 | 2023-06-28 | 2023-07-11 | 13 |  | 2 | 2023-07-13 | 20 | 2023-08-02 | 10 | 2023-08-12 | 59
2.108 | Lady Palm | 2023-07-06 | 2023-07-12 | 2023-07-25 | 13
2.108 | Monsterra | 2023-07-20 | 2023-07-26 | 2023-08-08 | 13 |  | 2 | 2023-08-10 | 20 | 2023-08-30 | 10 | 2023-09-09 | 59
2.109 | Never Never | 2023-08-03 | 2023-08-09 | 2023-08-22 | 13
2.109 | Orchid | 2023-08-17 | 2023-08-23 | 2023-09-05 | 13 |  | 9 | 2023-09-14 | 20 | 2023-10-04 | 10 | 2023-10-14 | 66
2.11 | Prayer | 2023-08-31 | 2023-09-06 | 2023-09-19 | 13
2.11 | Queen's Tear | 2023-09-14 | 2023-09-20 | 2023-10-03 | 13 |  | 2 | 2023-10-05 | 20 | 2023-10-25 | 10 | 2023-11-04 | 59
2.111 | Rubber | 2023-09-28 | 2023-10-04 | 2023-10-17 | 13
2.111 | String of Turtles | 2023-10-12 | 2023-10-18 | 2023-10-31 | 13 |  | 2 | 2023-11-02 | 20 | 2023-11-22 | 10 | 2023-12-02 | 59
2.112 | Ti | 2023-10-26 | 2023-11-01 | 2023-11-14 | 13
2.112 | Umbrella | 2023-11-09 | 2023-11-15 | 2023-11-28 | 13 |  | 9 | 2023-12-07 | 20 | 2023-12-27 | 10 | 2024-01-06 | 66
2.113 | Vine | 2023-11-23 | 2023-11-29 | 2023-12-12 | 13
2.113 | Weeping Fig | 2023-12-07 | 2023-12-13 | 2024-01-02 | 20 | Long Sprint | 9 | 2024-01-11 | 20 | 2024-01-31 | 10 | 2024-02-10 | 73
2.114 | Xanadu | 2023-12-28 | 2024-01-03 | 2024-01-23 | 20 | Long Sprint
2.114 | Yucca | 2024-01-18 | 2024-01-24 | 2024-02-06 | 13 |  | 2 | 2024-02-08 | 20 | 2024-02-28 | 10 | 2024-03-09 | 66
2.115 | Zebra | 2024-02-01 | 2024-02-07 | 2024-02-20 | 13
2.115 |  | 2024-02-15 | 2024-02-21 | 2024-03-05 | 13 |  | 9 | 2024-03-14 | 20 | 2024-04-03 | 10 | 2024-04-13 | 66
2.116 |  | 2024-02-29 | 2024-03-06 | 2024-03-19 | 13
2.116 |  | 2024-03-14 | 2024-03-20 | 2024-04-09 | 20 | Long Sprint | 2 | 2024-04-11 | 20 | 2024-05-01 | 10 | 2024-05-11 | 66
2.117 |  | 2024-04-04 | 2024-04-10 | 2024-04-23 | 13
2.117 |  | 2024-04-18 | 2024-04-24 | 2024-05-07 | 13 |  | 2 | 2024-05-09 | 20 | 2024-05-29 | 10 | 2024-06-08 | 59
2.118 |  | 2024-05-02 | 2024-05-08 | 2024-05-21 | 13
2.118 |  | 2024-05-16 | 2024-05-22 | 2024-06-04 | 13 |  | 2 | 2024-06-06 | 20 | 2024-06-26 | 10 | 2024-07-06 | 59
2.119 |  | 2024-05-30 | 2024-06-05 | 2024-06-18 | 13
2.119 |  | 2024-06-13 | 2024-06-19 | 2024-07-02 | 13 |  | 2 | 2024-07-04 | 20 | 2024-07-24 | 10 | 2024-08-03 | 59
2.12 |  | 2024-06-27 | 2024-07-03 | 2024-07-16 | 13
2.12 |  | 2024-07-11 | 2024-07-17 | 2024-07-30 | 13 |  | 2 | 2024-08-01 | 20 | 2024-08-21 | 10 | 2024-08-31 | 59
2.121 |  | 2024-07-25 | 2024-07-31 | 2024-08-13 | 13
2.121 |  | 2024-08-08 | 2024-08-14 | 2024-08-27 | 13 |  | 2 | 2024-08-29 | 20 | 2024-09-18 | 10 | 2024-09-28 | 59
2.122 |  | 2024-08-22 | 2024-08-28 | 2024-09-10 | 13
2.122 |  | 2024-09-05 | 2024-09-11 | 2024-09-24 | 13 |  | 2 | 2024-09-26 | 20 | 2024-10-16 | 10 | 2024-10-26 | 59
2.123 |  | 2024-09-19 | 2024-09-25 | 2024-10-08 | 13
2.123 |  | 2024-10-03 | 2024-10-09 | 2024-10-22 | 13 |  | 2 | 2024-10-24 | 20 | 2024-11-13 | 10 | 2024-11-23 | 59
2.124 |  | 2024-10-17 | 2024-10-23 | 2024-11-05 | 13
2.124 |  | 2024-10-31 | 2024-11-06 | 2024-11-19 | 13 |  | 2 | 2024-11-21 | 20 | 2024-12-11 | 10 | 2024-12-21 | 59
2.125 |  | 2024-11-14 | 2024-11-20 | 2024-12-03 | 13
2.125 |  | 2024-11-28 | 2024-12-04 | 2024-12-17 | 13 |  | 2 | 2024-12-19 | 20 | 2025-01-08 | 10 | 2025-01-18 | 59
2.126 |  | 2024-12-12 | 2024-12-18 | 2024-12-31 | 13
2.126 |  | 2024-12-26 | 2025-01-01 | 2025-01-14 | 13 |  | 2 | 2025-01-16 | 20 | 2025-02-05 | 10 | 2025-02-15 | 59
Formulas:
SOW Approval Date = [Sprint Start]-6
Sprint Start = [Sprint End, row above]+1
Sprint End = [Sprint Start]+20

## Editable Version 2020 (hidden)
Fix Version | Sprint Name | Sprint Start | Sprint End | Sprint Length | Days from Sprint End to UAT | UAT Release | Days until UAT Feedback Deadline | UAT Feedback Deadline + Regression Starts | Days Between UAT / Prod (UAT length) | Days Between UAT Signoff / Prod | Prod Release 4pm | Notes | Days UAT and Prod are the same
2.50.0 | App | 2018-10-24 | 2018-11-06 | 13
2.50.1 | Big Head | 2018-11-07 | 2018-11-20 | 13 | 16 | 2018-12-06 | 20 | 2018-12-26 | 37 | 17 | 2019-01-12 |  | -2
2.51.0 | Chicken | 2018-11-21 | 2018-12-11 | 20 | [7 empty] | Long Sprint
2.51.1 | Donkey | 2018-12-12 | 2019-01-01 | 20 | 9 | 2019-01-10 | 13 | 2019-01-23 | 30 | 17 | 2019-02-09 | Long Sprint, Moved for stat | -2
2.52.0 | Elephant | 2019-01-02 | 2019-01-15 | 13
2.52.1 | Fruitflies | 2019-01-16 | 2019-01-29 | 13 | 9 | 2019-02-07 | 20 | 2019-02-27 | 37 | 17 | 2019-03-16 |  | -16
2.53.0 | Gum | 2019-01-30 | 2019-02-12 | 13
2.53.1 | Homogenous | 2019-02-13 | 2019-02-26 | 13 | 2 | 2019-02-28 | 27 | 2019-03-27 | 44 | 17 | 2019-04-13 | Moved for stat | -9
2.54.0 | Induction | 2019-02-27 | 2019-03-12 | 13
2.54.1 | Jungle | 2019-03-13 | 2019-03-26 | 13 | 9 | 2019-04-04 | 20 | 2019-04-24 | 37 | 17 | 2019-05-11 | Moved for stat | -16
2.55.0 | Kite | 2019-03-27 | 2019-04-09 | 13
2.55.1 | Lagavulin | 2019-04-10 | 2019-04-23 | 13 | 2 | 2019-04-25 | 34 | 2019-05-29 | 51 | 17 | 2019-06-15 |  | -16
2.56.0 | Microminiturization | 2019-04-24 | 2019-05-07 | 13
2.56.1 | NULL | 2019-05-08 | 2019-05-21 | 13 | 9 | 2019-05-30 | 27 | 2019-06-26 | 44 | 17 | 2019-07-13 |  | -16
2.57.0 | Otter | 2019-05-22 | 2019-06-04 | 13
2.57.1 | Procrastinate | 2019-06-05 | 2019-06-18 | 13 | 9 | 2019-06-27 | 27 | 2019-07-24 | 44 | 17 | 2019-08-10 |  | -16
2.58.0 | Quoll | 2019-06-19 | 2019-07-02 | 13
2.58.1 | Releasable | 2019-07-03 | 2019-07-16 | 13 | 9 | 2019-07-25 | 34 | 2019-08-28 | 51 | 17 | 2019-09-14 |  | -23
2.59.0 | Sun | 2019-07-17 | 2019-07-30 | 13
2.59.1 | Troglodyte | 2019-07-31 | 2019-08-13 | 13 | 9 | 2019-08-22 | 41 | 2019-10-02 | 58 | 17 | 2019-10-19 | Moved for stat | -30
2.60.0 | Unresponsive | 2019-08-14 | 2019-08-27 | 13
2.60.1 | Vulture | 2019-08-28 | 2019-09-10 | 13 | 9 | 2019-09-19 | 41 | 2019-10-30 | 58 | 17 | 2019-11-16 | Moved for stat | -30
2.61.0 | Why | 2019-09-11 | 2019-09-24 | 13
2.61.1 | Xylophone | 2019-09-25 | 2019-10-08 | 13 | 9 | 2019-10-17 | 34 | 2019-11-20 | 51 | 17 | 2019-12-07 |  | -23
2.62.0 | Yellow | 2019-10-09 | 2019-10-22 | 13
2.62.1 | Zebra | 2019-10-23 | 2019-11-05 | 13 | 9 | 2019-11-14 | 41 | 2019-12-25 | 58 | 17 | 2020-01-11 |  | -16
2.63.0 | Able | 2019-11-06 | 2019-11-19 | 13
2.63.1 | Best | 2019-11-20 | 2019-12-10 | 20 | 16 | 2019-12-26 | 27 | 2020-01-22 | 44 | 17 | 2020-02-08 | Long Sprint, Moved for stat | -9
2.64.0 | Cold | 2019-12-11 | 2019-12-31 | 20 | [7 empty] | Long Sprint
2.64.1 | Deep | 2020-01-01 | 2020-01-14 | 13 | 16 | 2020-01-30 | 27 | 2020-02-26 | 44 | 17 | 2020-03-14
Formulas:
Sprint End = [Sprint Start]+13
Sprint Start = [Sprint End, row above]+1

## 1st Draft (hidden)
Fix Version | Sprint Name | Sprint Start | Sprint End | Sprint Length | Days from Sprint End to UAT | UAT Release | Days until UAT Feedback Deadline | UAT Feedback Deadline + Regression Starts | Days Between UAT / Prod (UAT length) | Days Between UAT Signoff / Prod | Prod Release 4pm | Notes | Days UAT and Prod are the same
2.50.0 | App | 2018-10-24 | 2018-11-06 | 13
2.50.1 | Big Head | 2018-11-07 | 2018-11-20 | 13 | 16 | 2018-12-06 | 20 | 2018-12-26 | 37 | 17 | 2019-01-12 |  | -2
2.51.0 | Chicken | 2018-11-21 | 2018-12-11 | 20 | [7 empty] | Long Sprint
2.51.1 | Donkey | 2018-12-12 | 2019-01-01 | 20 | 9 | 2019-01-10 | 13 | 2019-01-23 | 30 | 17 | 2019-02-09 | Long Sprint, Moved for stat | -2
2.52.0 | Elephant | 2019-01-02 | 2019-01-15 | 13
2.52.1 | Fruitflies | 2019-01-16 | 2019-01-29 | 13 | 9 | 2019-02-07 | 20 | 2019-02-27 | 37 | 17 | 2019-03-16 |  | -16
2.53.0 | Gum | 2019-01-30 | 2019-02-12 | 13
2.53.1 | Homogenous | 2019-02-13 | 2019-02-26 | 13 | 2 | 2019-02-28 | 27 | 2019-03-27 | 44 | 17 | 2019-04-13 | Moved for stat | -9
2.54.0 | Induction | 2019-02-27 | 2019-03-12 | 13
2.54.1 | Jungle | 2019-03-13 | 2019-03-26 | 13 | 9 | 2019-04-04 | 20 | 2019-04-24 | 37 | 17 | 2019-05-11 | Moved for stat | -16
2.55.0 | Kite | 2019-03-27 | 2019-04-09 | 13
2.55.1 | Lagavulin | 2019-04-10 | 2019-04-23 | 13 | 2 | 2019-04-25 | 34 | 2019-05-29 | 51 | 17 | 2019-06-15 |  | -16
2.56.0 | Microminiturization | 2019-04-24 | 2019-05-07 | 13
2.56.1 | NULL | 2019-05-08 | 2019-05-21 | 13 | 9 | 2019-05-30 | 27 | 2019-06-26 | 44 | 17 | 2019-07-13 |  | -16
2.57.0 | Otter | 2019-05-22 | 2019-06-04 | 13
2.57.1 | Procrastinate | 2019-06-05 | 2019-06-18 | 13 | 9 | 2019-06-27 | 27 | 2019-07-24 | 44 | 17 | 2019-08-10 |  | -16
2.58.0 | Quoll | 2019-06-19 | 2019-07-02 | 13
2.58.1 | Releasable | 2019-07-03 | 2019-07-16 | 13 | 9 | 2019-07-25 | 34 | 2019-08-28 | 51 | 17 | 2019-09-14 |  | -23
2.59.0 | Sun | 2019-07-17 | 2019-07-30 | 13
2.59.1 | Troglodyte | 2019-07-31 | 2019-08-13 | 13 | 9 | 2019-08-22 | 41 | 2019-10-02 | 58 | 17 | 2019-10-19 | Moved for stat | -30
2.60.0 | Unresponsive | 2019-08-14 | 2019-08-27 | 13
2.60.1 | Vulture | 2019-08-28 | 2019-09-10 | 13 | 9 | 2019-09-19 | 41 | 2019-10-30 | 58 | 17 | 2019-11-16 | Moved for stat | -30
2.61.0 | Why | 2019-09-11 | 2019-09-24 | 13
2.61.1 | Xylophone | 2019-09-25 | 2019-10-08 | 13 | 9 | 2019-10-17 | 34 | 2019-11-20 | 51 | 17 | 2019-12-07 |  | -23
2.62.0 | Yellow | 2019-10-09 | 2019-10-22 | 13
2.62.1 | Zebra | 2019-10-23 | 2019-11-05 | 13 | 9 | 2019-11-14 | 41 | 2019-12-25 | 58 | 17 | 2020-01-11 |  | -16
2.63.0 | Able | 2019-11-06 | 2019-11-19 | 13
2.63.1 | Best | 2019-11-20 | 2019-12-10 | 20 | 16 | 2019-12-26 | 27 | 2020-01-22 | 44 | 17 | 2020-02-08 | Long Sprint, Moved for stat | -9
2.64.0 | Cold | 2019-12-11 | 2019-12-31 | 20 | [7 empty] | Long Sprint
2.64.1 | Deep | 2020-01-01 | 2020-01-14 | 13 | 16 | 2020-01-30 | 27 | 2020-02-26 | 44 | 17 | 2020-03-14
Formulas:
Sprint End = [Sprint Start]+13
Sprint Start = [Sprint End, row above]+1